## Risks
Risk Name | Risk Description | Risk Probability of Occurrence | Risk Impact | Risk Factor | Risk Mitigation | Person in Charge of Tracking
Sudden sickness | If one of the developers gets sick and won't be able to continue developing for the project | 5% | 6 | 0.3 | Constant inclusion of atleast one further team member into your own codebase | Everyone
Not enough time | Under erstimating the time needed for certain tasks | 15% | 10 | 1.5 | Keeping track of time management | Everyone
Sudden change of software | Flutter is a beta software, it might change without any further notice and break something | 50% | 7 | 3.5 | Stay uptodate on software blogs and news | Dennis, Joschua
Docker/Server break down | Because of unpredictable issues we might encountered unexpected errors | 40% | 9 | 3.6 | Always have backups of our images | Duc, Joschua
Productivity issues | Procrastination and productivity of certain people might occure | 33% | 5 | 1.65 | Team members try to motivate and keep an eye on each other | Everyone
Cyber attacks | People trying to hurt us and our environment | 5% | 9 | 0.45 | Always have backups of our databases and writing of unhackable software | Everyone
Dataprivacy | Sudden change of guidelines and policies | 50% | 1 | 0.5 | Keep an eye on the news and certain other sources | Everyone
UseCases last semester
UC | Documentation | Coding | Testing | Warm-Up time | Total | FP
create Account | 10 | 25 | 10 | 7 | 52
log into account | 12 | 20 | 10 | 7 | 49
add item to fridge | 2 | 3 | 2 | 5 | 12
remove item from fridge | 2 | 3 | 2 | 3 | 10
get the items in the fridge | 2 | 6 | 4 | 3 | 15
UseCases this semester
UC | Documentation est. | Coding est. | Testing est. | Warm-Up time est. | Total est. | FP
manage account | 3 | 1 | 2 | 2 | 8
delete account | 1 | 4 | 3 | 3 | 11
join fridge | 1 | 4 | 4 | 1 | 10
remove user from fridge | 1 | 1 | 1 | 1 | 4
sync fridge | 3 | 2 | 3 | 1 | 9
invite user to fridge | 1 | 1 | 3 | 3 | 8
add admin | 4 | 2 | 1 | 3 | 10
remove user from fridge | 4 | 4 | 3 | 3 | 14
remove admin | 1 | 2 | 4 | 3 | 10
edit fridge information | 2 | 2 | 1 | 1 | 6